## NWA (hidden)
DETAILED IMPLEMENTATION PLAN
ACTIVITY/Project NAME |  |  | Project Alapaap - WS2 Sprint 4
IMPLEMENTATION DATE |  |  | 2025-05-21
PREPARED BY |  |  | WS2 Leads
REVIEWED BY
CREATED DATE |  |  | 2025-05-19
Task |  |  | Date | Estimated Time to Complete (hr) | Target |  | Actual |  | Remarks / Status | In-charge
[5 empty] | Start Time | End Time | Start Time | End Time
ACTIVITY PROPER
WS2 - Sprint 4 Release (main/release-v3.0.0)
Details: a. Deployment of new jobs in databricks 1. DEVICES Calamity Report 2. DEVICES DEPED MINS 3. DEVICES MNC/MCC 4. Daily 4G QOS Utilization 5. VLR (eSA - Users) 6. TNT TX Reports 7. RAN_ASSETINVENTORY 8. RANBIS 9. HISTOGRAM 10. DEVICES NMS 11. Data Funnel 12. Devices Geo 1
b. Implementation of meta_r schema and DynamoDB
c. KPI Conditioning Enhancement
1 | Prework | Pull request approval from WS Lead (PLDT/Smart) from staging to main branch | 2025-05-21 | 0.1 |  |  | 10:40 | 10:50 | Completed | Smart Devs | Pre work: Prod configs and shell script
2 | Prework | Creation of Teams Channel for DQ Check Results | 2025-05-21 | 0.05 |  |  | 11:00 | 11:05 | Completed | Meann Simbahan
3 | Prework | Editing of secrets in AWS Secrets Manager for Webhook URL | 2025-05-21 | 0.05 |  |  | 11:05 | 11:10 | Completed | Meann Simbahan
4 | Deployment | New release/tag creation from main branch on github and CI/CD triggering | 2025-05-21 | 0.1 |  |  | 10:50 | 11:00 | Completed | Smart Main Dev
5 | Deployment | Databricks Assets Bundle deployment from github | 2025-05-21 | 0.3 |  |  | 11:00 | 11:30 | Completed | Automated once release is created (Item #2)
6 | Deployment | Validate the asset by checking the tables, jobs and codebase present in the SP's workspace | 2025-05-21 | 0.1 |  |  | 11:30 | 11:52 | Completed | Smart Devs/Smart L2
7 | Deployment | Validate databricks S3 path mapping table for lambda trigger | 2025-05-21 | 0.05 |  |  | 11:52 | 11:54 | Completed | Smart Devs/Smart L2
8 | Deployment | Publish updated DQ and Ops Dashboard in NA_PROD environment | 2025-05-21 | 0.05 |  |  | 11:54 | 12:00 | Completed | Smart Devs
9 | Deployment | Enable lakehouse monitor for the required table | 2025-05-21 | 0.1 |  |  | 12:00 | 12:00 | Completed | Smart Devs
10 | Deployment | Grant service principal full access permission to lakehouse created table/s | 2025-05-21 | 0.1 |  |  | 12:00 | 12:00 | Completed | Smart Devs
11 | Deployment | Turn on new cron jobs in Datasync01 for file transfer to S3 | 2025-05-21 | 0.1 |  |  | 12:00 | 12:20 | Completed | Smart Devs
12 | Deployment | Move ref logs from meta_b to meta_r | 2025-05-21 | 1 |  |  | 12:20 | 15:10 | Completed | Smart Devs | reference only
13 | Post Validation Back tracking | Parallel Test: Run each file movement job in datasync to trigger job in DBX | May 21 - June 6 | 1.25 |  |  | 16:25 |  | Ongoing | Smart Devs
ROLLBACK
Revert Plan
14 |  | Go to the Github and checkout to the previous release version and check its successful github action |  | 0.05 | [5 empty] | Smart Devs
15 |  | Run the deployment from previous release version from Github Action |  | 0.3 | [5 empty] | Smart Devs
16 |  | Validate the jobs from the SP workspace, it should have the older release jobs |  | 0.1 | [5 empty] | Smart Devs
Total Number of Hours

## WDE Implementation Plan
DETAILED IMPLEMENTATION PLAN
ACTIVITY/Project NAME |  |  | Project Alapaap - WDE GENZ PIPELINE
IMPLEMENTATION DATE |  |  | 2025-08-13
PREPARED BY |  |  | WS2 Leads
REVIEWED BY |  |  | Meann Simbahan
CREATED DATE
Task |  |  | Date | Estimated Time to Complete (hr) | Target |  | Actual |  | Remarks / Status | In-charge
[5 empty] | Start Time | End Time | Start Time | End Time
ACTIVITY PROPER
WDE - Release (main/)
Details: a. Deployment of new jobs in databricks 1) cox_sms 2) cox_data 3) cox_call 4) cox_byte
1 | Prework | Pull request approval from WS Lead (PLDT/Smart) from staging to main branch | [6 empty] | Completed | Smart Devs kenny
2 | Deployment | New release/tag creation from main branch on github and CI/CD triggering | [6 empty] | Completed | kenny
3 | Deployment | Databricks Assets Bundle deployment from github | [6 empty] | Completed | Automated once release is created (Item #2)
4 | Deployment | Validate the asset by checking the tables, jobs and codebase present in the SP's workspace | [6 empty] | Completed | Smart Devs/Smart L2
6 | Deployment | Create new function table | [6 empty] | Completed | kenny
7 | Deployment | Create PII Tags for each newly created tables | [6 empty] | Completed | kenny
8 | Post Validation Back tracking | Post Production Test: Run each file movement job in datasync to trigger job in DBX | [6 empty] | Completed | Smart Devs
ROLLBACK
Revert Plan
12 |  | Go to the Github and checkout to the previous release version and check its successful github action | [7 empty] | Smart Devs
13 |  | Run the deployment from previous release version from Github Action | [7 empty] | Smart Devs
14 |  | Validate the jobs from the SP workspace, it should have the older release jobs | [7 empty] | Smart Devs
Total Number of Hours